## Risk Assessment Table
Risk Category | Hazards | Inherent Risk |  |  | Control Measures | Residual Risk
|  | Likelihood | Consequence | Risk rating |  | Likelihood | Consequence | Risk rating
Technical | Multipath Propagation and Acoustic Distortion There are reflections from the seafloor or water surface which can cause multipath effects, leading to ambiguous or inaccurate distance measurements. | Likely | Major | Extreme (20) | • Develop echo suppression algorithms to filter out delayed reflections. • Conduct regular signal integrity testing to detect multipath effects early. | Possible | Minor | Medium (9)
Technical | Signal Interference and Beacon Collision With multiple (three) beacons operating in the same frequency range, there might be signal collisions which could lead to inaccurate range measurements or even communication failure. | Likely | Catastrophic | Extreme (24) | • Implement time-division multiplexing (TDM) or frequency hopping techniques to reduce interference. • Ensure beacon transmissions are synchronized to avoid overlap. | Unlikely | Minor | Medium (6)
Reliability | Power Consumption and Battery Life Running multiple beacons simultaneously increases the power demand, which could limit the operational time. | Likely | Moderate | High (16) | • Optimize beacon transmission intervals and use low-power modes for inactive beacons. • Establish guidelines for efficient power management during operations. | Possible | Minor | Medium (9)
Reliability | Data Integrity and Loss Prevention If there are transmission errors or beacon failures, it could result in lost or corrupted data, which leads to inaccurate positioning. | Possible | Catastrophic | Extreme (23) | • Use Forward Error Correction (FEC) and Cyclic Redundancy Checks (CRC) to validate received data. • Implement real-time monitoring and alerts for transmission failures. | Unlikely | Major | High (17)
Security | Unauthorized Signal Spoofing Any unintended acoustic sources could spoof the beacon signals and this disrupt navigation and positioning of the ROV. | Unlikely | Catastrophic | High (19) | • Implement cryptographic authentication mechanisms to validate beacon signals. • Train personnel on detecting and reporting anomalies in acoustic signals. | Unlikely | Major | High (17)
Safety | Impact on Marine Life Sonar emissions might disturb some marine life, particularly the species that are sensitive to acoustic signals. | Possible | Minor | Medium (9) | • Adjust sonar frequencies to biologically safe thresholds. • Follow marine safety regulations and perform impact assessments. • Use noise-dampening equipment where applicable. | Rare | Insignificant | Low (1)
Other | Limited Access to Testing Facilities Availability of suitable underwater testing environments like a pool may be constrained and this can delay our progress in the later stages. | Possible | Moderate | High (15) | • Plan for alternative testing sites ahead of time. • Use simulation environments to replace real-world testing where feasible. • Schedule backup testing sessions to avoid delays. | Unlikely | Moderate | Medium (8)
Other | Difficulty Contacting Client for Feedback The client may be slow to respond to emails or messages, causing delays in getting feedback or approvals, which can affect project progress and decision-making. | Unlikely | Moderate | Medium (8) | • Establish multiple communication channels e.g. email, phone, video calls. • Assign a team member as the main point of contact to follow up regularly. | Unlikely | Minor | Medium (6)
Other | Group Member Sick or Unavailable for Key Work A team member may fall sick or be unavailable due to personal reasons, leading to delays in completing assigned tasks and increased workload for others. | Unlikely | Moderate | Medium (8) | • Assign backup members for critical tasks in advance. • Maintain clear documentation so another team member can take over if needed. • Set early deadlines to allow buffer time for unexpected absences. | Unlikely | Minor | Medium (6)

## List
Technical | Almost certain | Catastrophic |  | Insignificant | Minor | Moderate | Major | Catastrophic
Reliability | Likely | Major | Almost Certain | Medium (10) | High (14) | Extreme (21) | Extreme (22) | Extreme (25)
Security | Possible | Moderate | Likely | Medium (7) | High (13) | High (16) | Extreme (20) | Extreme (24)
Safety | Unlikely | Minor | Possible | Low (4) | Medium (9) | High (15) | High (18) | Extreme (23)
Other | Rare | Insignificant | Unlikely | Low (2) | Medium (6) | Medium (8) | High (17) | High (19)
|  |  | Rare | Low (1) | Low (3) | Low (5) | Medium (11) | Medium (12)
Don’t change anything on this sheet